## All FY20
O&M DREDGING PLAN FOR FY20*
Project | District | Adv./Open Bids Dates | 2019 |  |  | 2020 | [11 empty] | Volume | Placement Site | Notes
|  |  | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
|  |  | FY 2020 | [11 empty] | FY 2021
Alaska District (POA)
Anchorage Harbor (Hopper or Mechanical) | POA | N/A | [15 empty] | 1.1 MCY/YR | In-Water | Includes option to dredge Cook Inlet Nav. Channel & Anchorage spring dredging.
Aurora & Harris Harbors | POA | N/A | [15 empty] | 30.9 KCY | In-Water | Included with breakwater repairs for two harbors in Juneau, AK.
Dillingham Harbor (Suction Cutterhead) | POA | Oct/Nov 2019 | [15 empty] | 110 KCY/YR | In-Water | New 3-year maintenance contract. Preference to complete dredging by 30 June.
Homer & Ninilchik Harbors (Suction Cutterhead) | POA | N/A | [15 empty] | 27 KCY/YR | Upland | Existing contract.
Homer & Ninilchik Harbors (Suction Cutterhead) | POA | Nov/Dec 2019 | [15 empty] | 25 KCY/YR | Upland | New 3-year contract. Env. windows vary by location and overlap. Options for USCG Berth.
Nome Harbor (Suction Cutterhead) | POA | N/A | [15 empty] | 69 KCY/YR | Beach | Dredging within inner harbor to be completed by 30 June env. window. | bar: 2020 JUN
Honolulu District (POH)
Nawiliwili Harbor (Mechanical) | POH | Aug/Sep 2018 | [15 empty] | 110 KCY | In-Water | Placement in the Nawiliwili EPA ODMDS
Honolulu Harbor (Mechanical) | POH | Apr/May 2020 | [15 empty] | 140 KCY | Upland and In-Water | 15% of material placed in landfill, rest placed in the Oahu EPA ODMDS
Port Allen Harbor (Mechanical) | POH | May/Jun 2020 | [15 empty] | 440 KCY | In-Water | Placement in the Port Allen EPA ODMDS
Seattle District (NWS)
FY18-20 Grays Harbor Inner Harbor (Mechanical) | NWS | N/A | [15 empty] | 650 KCY per work window | Open Water - Pt. Chehalis, South Jetty | Work window 15 Jul - 14 Feb | bar: 2019 OCT to 2020 FEB; 2020 JUL to 2020 DEC
FY19 Snohomish/Everett (Hydraulic) | NWS | N/A | [15 empty] | 150 KCY | Upland - Site O, Jetty Island | Work Window 15 Oct - 14 Feb | bar: 2019 OCT to 2020 FEB; 2020 OCT to 2020 DEC
FY19 Quillayute River (Hydraulic) | NWS | N/A | [15 empty] | 55 KCY | Upland - Rialto Spit | Work Window 1 Sep - 29 Feb | bar: 2019 OCT to 2020 FEB; 2020 SEP to 2020 DEC
FY19 Duwamish (Mechanical) | NWS | N/A | [15 empty] | 65 KCY | Open Water - Elliot Bay | Work Window 1 Dec - 16 Jan | bar: 2019 OCT to 2020 FEB; 2020 OCT to 2020 DEC
FY19 Bellingham - Squalicum WW (Mechanical) | NWS | N/A | [15 empty] | 165 KCY | Open Water - Rosario, Port Gardner | Work Window 1 Oct - 14 Feb | bar: 2019 OCT to 2020 FEB; 2020 OCT to 2020 DEC
FY20 Grays Harbor Outer Harbor (Hopper) | NWS | N/A | 2020 MAR: YAQUINA; 2020 JUN: ESSAYONS | 700 KCY | Open Water - SBDS, HMB, Pt. Chehalis | Work window 1 Apr - 31 May
FY21-FY23 Grays Harbor Inner Harbor (Mechanical) | NWS | Aug/Sep 2020 | [15 empty] | 700 KCY per work window | Open Water - SJDS, Pt. Chehalis | Work window 15 Jul - 14 Feb; Contract Start 1 Dec | bar: 2019 OCT to 2020 FEB; 2020 JUL to 2020 DEC
FY20 Snohomish/Everett (Mechanical) | NWS | Aug/Sep 2020 | [15 empty] | 150 KCY | Open Water - Port Gardner | Work window 16 Oct - 14 Feb | bar: 2019 OCT to 2020 FEB; 2020 OCT to 2020 DEC
FY20 Kenmore (Mechanical) | NWS | Aug/Sep 2020 | [15 empty] | 30 KCY | Upland - Subtitle D | Work window 1 Nov - 14 Feb | bar: 2019 NOV to 2020 FEB; 2020 NOV to 2020 DEC
FY20 Keystone (Mechanical) | NWS | Aug/Sep 2020 | [15 empty] | 35 KCY | Upland - beach nourishment | Work window 15 Jul - 15 Feb | bar: 2019 OCT to 2020 FEB; 2020 JUL to 2020 DEC
Portland District (NWP)
Columbia River Side Channels Clamshell | NWP | N/A | [15 empty] | 340 KCY -'19 | In-Water | (9) Projects | bar: 2020 MAY to 2020 OCT
OR/WA Coast Clamshell | NWP | Apr/May 2020 | [15 empty] | 270 KCY -'19 180 KCY - '20 | In-Water | (6) Projects - '19 / (3) Projects- '20 | bar: 2020 MAY to 2020 OCT
Garibaldi - Depoe Bay Pipeline | NWP | N/A | [15 empty] | 65 KCY | In-Water / Surfzone | bar: 2020 MAY to 2020 OCT
Dredge OREGON Rental (Suction Cutterhead) | NWP | Sole Source Port of Portland | [15 empty] | 1.9 MCY | In-Water and Upland | 10-year contract in place (AWD: 9/2017)
MCR and CLW (Hopper) | NWP | Jan/Feb 2020 | 2019 NOV: WCH 2019; 2020 MAY: WCH 2020 | 3.9 MCY-'19 3.9 MCY-'20 | In-Water | West Coast Hopper Contract (up to 3.9mcy in '20)
Oregon Coast | NWP | N/A | 2019 NOV: YAQUINA; 2020 MAR: YAQUINA | 730 KCY | In-Water | Work windows vary by project
CLW and VTD | NWP | N/A | 2020 MAR: YAQUINA | 915 KCY | In-Water
Coos Bay Entrance | NWP | N/A | 2020 JUN: ESSAYONS | 700 KCY | In-Water
MCR and CLW | NWP | N/A | 2020 MAR: ESSAYONS | 3.9 MCY | In-Water
Walla Walla District (NWW)
|  | N/A | [17 empty] | No planned dredging in FY20 | bar: 2019 DEC to 2020 MAR; 2020 DEC
San Francisco District (SPN)
SF Main Ship Channel | SPN/NWP | N/A | 2019 OCT: ESSAYONS; 2020 JUN: ESSAYONS | 370kcy-'19 350Kcy-'20 | OBDS/ SF-8 | Essayons
Humboldt Bar & Entrance (Hopper) | SPN/NWP | N/A | 2020 JUL: WCH Contract 2020 | 1.2 KCY-'19 / 1 MCY-'20 | HOODS
Pinole Shoal | SPN/NWP | N/A | [17 empty] | Deferred for FY20 | bar: 2019 OCT to 2019 NOV; 2020 JUN to 2020 NOV
Crescent City | SPN | Jun/Jul 2020 | [17 empty] | FY19 Project | bar: 2019 OCT to 2019 NOV; 2020 AUG to 2020 NOV
Redwood City Harbor | SPN | Apr/May 2020 | [17 empty] | FY19 Project | bar: 2019 OCT to 2019 NOV; 2020 JUN to 2020 NOV
Richmond Inner Harbor | SPN | Mar/Apr 2020 | [15 empty] | 350 KCY | DODS/upland least cost | IFB | bar: 2019 OCT to 2019 NOV; 2020 JUN to 2020 NOV
Combined Sac/San Joaquin | SPN | Apr/May 2020 | [15 empty] | 350 KCY | Various Upland | IFB | bar: 2019 OCT to 2019 NOV; 2020 JUL to 2020 NOV
Oakland Harbor | SPN | Mar/Apr 2020 | [15 empty] | 750 KCY | DODS/upland least cost | IFB | bar: 2019 OCT to 2019 NOV; 2020 AUG to 2020 NOV
Suisun Bay Channel | SPN | Jun/Jul 2020 | [15 empty] | 130 KCY | SF-16 | Motco is being assessed as an additonal stand alone contract | bar: 2019 OCT to 2019 NOV; 2020 AUG to 2020 NOV
Richmond Outer Harbor | SPN/NWP | N/A | 2020 JUL: ESSAYONS | 300 KCY | SF-11 / SF-10
Los Angeles District (SPL)
Santa Barbara Harbor (Suction Cutterhead) | SPL | Oct/Nov 2019 | [15 empty] | 250 KCY | Beach | Multi-Year Contract | bar: 2019 OCT to 2020 APR; 2020 OCT to 2020 DEC
Channel Islands Harbor (Suction Cutterhead) | SPL | N/A | [15 empty] | 1.8 MCY | Beach | Multi-Year Contract | bar: 2019 OCT to 2020 MAR; 2020 OCT to 2020 DEC
Port Hueneme Deepening (Sec 107) (Suction Cutterhead or Mechanical) | SPL | Jan/Feb 2020 | [15 empty] | 400 KCY | Beach/Nearshore | As a part of the deepening contract
Ventura Harbor (Suction Cutterhead) | SPL | N/A | [15 empty] | 600 KCY | Beach | Multi-Year Contract | bar: 2019 OCT to 2020 MAR; 2020 OCT to 2020 DEC
Los Angeles River Estuary LA-LB Harbor (Mechanical) | SPL | Dec/Jan 2020 | [15 empty] | 200 KCY | Ocean
Oceanside Harbor (Suction Cutterhead) | SPL | N/A | [15 empty] | 350 KCY | Beach | Multi-Year Contract
San Diego Harbor (Suction Cutterhead or Mechanical) | SPL | Aug/Nov 2019 | [15 empty] | 250 KCY | Beach | Bid Opening delayed due to environmental issues | bar: 2019 OCT to 2020 APR; 2020 OCT to 2020 DEC
Morro Bay | SPL/NWP | N/A | 2020 APR: YAQUINA | 130 KCY | NSDS
| Italics | [18 empty] | Abbreviations: | bar: 2020 NOV to 2020 DEC
Advertise/Award | Subject to Funding |  | 2019 OCT: New Contract; 2020 FEB: Complete & Ongoing Contracts; 2020 JUL: Gov't Dredge; 2020 NOV: Environmental Window |  |  | WCH - West Coast Hopper
* Based on FY20 President's Budget | [17 empty] | Updated: | 2019-10-29