## Slide 1: Planning Habitat Restoration for Dredging Projects
WEDA Midwest Chapter Conference
Green Bay, Wisconsin
April 27, 2012
Jack Brunner
Notes: Discuss approach and considerations when planning habitat restoration for dredging projects

## Slide 2: Outline
Advantages of Habitat Restoration
Planning Considerations
Grand Calumet River: Case Study
Lessons Learned
Summary

## Slide 3: Advantages of Habitat Restoration
Wildlife and Ecosystem Benefits
Community Relations
Program Priority - EPA, USACE, and State
Permitting Requirements
Cost Savings
Notes: Planned wildlife/ecosystem benefits as well as additional (submergent resergence at wolf lake with better wave/hydrology)
Community appreciates
Now a priority for programs (GLLA authorized for habitat restoration)
Satisfy mitigation or other permitting requirements
Cost savings (eg, geotextile tubes provide disposal and can be used to create islands/habitat)

## Slide 4: Planning Considerations: Assessment Factors
Notes: GRAPHIC showing individual factors to assess during planning

## Slide 5: Planning Considerations: Project Components
Stakeholders
Funding/Authority
Site Access
Substrate
Hydrology
Vegetative Communities
Notes: Look at similar project components within each of these factors
Input from funding and regulatory agencies; surrounding property owners(future land use)
Limitations of program authority and funding – GLLA not previously authorized for habitat restoration
Property access and utility restrictions
Substrate suitability – provide or amend (variability at wolf lake)
Define hydrology and adjust plans accordingly (temporary measures for installation)
Determine suitable communities based on substrate and habitat

## Slide 6: Planning Considerations: Project Components
Planting Strategy
Performance Standards
T&E Species
Invasive Species
Predator Control
Maintenance
Notes: Tailor planting strategy toward existing and proposed conditions (hydrology/substrate), considering implementability
Reasonable performance standards
Consult and accommodate TES
Consider invasive species threats – treat and maintain
Protect from predators

## Slide 7: Planning Considerations
Notes: GRAPHIC shows and overlap of site the site components that need to be assessed when looking at:
Existing site conditions
Restoration goals
Implementation challenges

## Slide 8: Grand Calumet River
Great Lakes Legacy Act project
EPA GLNPO, USFWS and State of Indiana
Grand Calumet River AOC, Lake County, IN
Notes: Discuss WBGCR and how lessons learned applied to EBGCR.

## Slide 9: WBGCR Reaches 1 & 2 and Roxana Marsh
Restoration goals
  Excavate ~109,000 CY of contaminated sediment from 19-acre marsh
  Dredge river and wetland shelves
  Remove invasive species
  Restore native habitat
  Stabilize banks
Construction substantially complete: June 2012

## Slide 10: West Branch Reaches 1 & 2 and Roxana Marsh

## Slide 11: Roxana Marsh – Restoration Plan

## Slide 12: Invasive Species Control
Sprayed Phragmites in non-dredge areas
Utility and other access limitations

## Slide 13: Marsh Excavation
Removed Phragmites root mass with contamination
Used road mats for access

## Slide 14: Marsh Excavation

## Slide 15: Marsh Excavation

## Slide 16: River Dredging
Undercut Phragmites along banks
Removed from the site

## Slide 17: Sand Capping
Placed hydraulically in river
Placed mechanically in marsh and wetland shelves
Notes: Better tolerance achieved mechanically
Nice “Natural variability in some areas with capping

## Slide 18: Mowing
Prescribed burn restrictions
Mowed after herbicide application

## Slide 19: Raking or Tilling
Tilled to improve seed to soil contact
Depth limitations in pipeline buffer areas
Raked as needed

## Slide 20: Seeding and Planting
Adjust planting zones based on as-built conditions
Blanket seeded areas
Notes: Pic of final graded areas –marsh

## Slide 21: Providing Habitat Structure
Removed trees for site access
Placed within pond and along shoreline as habitat structure
Notes: ADD PIC OF STAGED TREES
Pile and temp placement of debris

## Slide 22: Bank Stabilization
Used bioengineering techniques
Modified design based on field conditions
Notes: Before/after pics of bank restoration

## Slide 23: EBGCR Reaches 4A and 4B

## Slide 24: EBGCR Reaches 4A and 4B

## Slide 25: Lessons Learned
Involve stakeholders early in planning
Spray invasives before sediment removal
Use prescribed burning where possible
Adjust planting zones as needed
Blanket seeded areas
Install and maintain predator control fencing

## Slide 26: Summary
Consider assessment factors and project components during planning and design
Employ adaptive management during project implementation
Restoration takes time

## Slide 27: Questions?
Jack Brunner
Tetra Tech
jack.brunner@tetratech.com
312.201.7788